|  |
| --- |
| ERASMUS+ PROGRAMME  Project Number: 574010-EPP-1-2016-1-JO-EPPKA2-CBHE-JP |
| **FOODQA - Fostering Academia-Industry Collaboration in Food Safety and Quality** |
| Planning of WP4: PILOT OF IMPLEMENTATION OF FOOD SAFETY AND QUALITY MANAGEMENT SYSTEMS – Pilot Studies no. 3 and no. 4 |
| C:\Users\Dr\Downloads\FoodQA\th.jpg |
| Creative Thinking Development |
| **September 2018** |

# Project Team

|  |  |
| --- | --- |
| **LEADER: Creative Thinking Development (CRE.THI.DEV.)** | |
| **Name** | **E mail address** |
| Papakonstantinou Dimosthenis | [dpapakon7@yahoo.gr](mailto:dpapakon7@yahoo.gr) |
| Papakonstantinou Sofia | spapakon@hotmail.com |
| Lina Tsakalou | [ltsakalou@gmail.com](mailto:ltsakalou@gmail.com) |
| **The University of Jordan (UJ)** | |
| **Name** | **E mail address** |
| Prof. Ahmed Al-Salaymeh | salaymeh@ju.edu.jo |
|  |  |
|  |  |
| **Jordan Food and Drugs Administration (JFDA)** | |
| **Name** | **E mail address** |
| Dr. Amjad Haymour | [amjad.haymour@jfda.jo](mailto:amjad.haymour@jfda.jo) |
| Eng. Safa Al-Smadi | [safa.smadi@jfda.jo](mailto:safa.smadi@jfda.jo)  [smadi.safa@gmail.com](mailto:smadi.safa@gmail.com) |
|  |  |
| **University of Split (UNIST)** | |
| **Name** | **E mail address** |
| Prof. Josipa Giljanovic | josipa@ktf-split.hr |
| Prof. Ante Prkic | [prkic@ktf-split.hr](mailto:prkic@ktf-split.hr) |
|  |  |
|  |  |

# Planning of Activities

## 2.1 Pilot companies no. 3 & 4

|  |  |  |
| --- | --- | --- |
| **WP4.2 – IMPLEMENTATION OF FOOD SAFETY AND QUALITY MANAGEMENT SYSTEMS** | | |
| **PERIOD** | **ACTIVITY** | **PARTICIPANTS** |
| 1-15/9/18 | Preparation of initial questionnaire for the company (the questionnaire should include company’s letter of commitment, general information about company’s activities/products, documents already used in the application of HACCP, etc.) | EU + Jordanian partners |
| 15-30/9/18 | Completion of questionnaire and additional information | Company (supported by Jordanian partners) |
| 1/10-31/12/18 | Evaluation of questionnaire and initial assessment | EU + Jordanian partners |
| Preparation of requested food safety management system according to the standard requirements. | EU + Jordanian partners |
| Communication between local partners and company for any matters concerning the adaptation of the standard to the company. | Jordanian partners + company |
| Monthly follow-up concerning the preparation/progress of the selected Food safety management system. | AUA and BAU |
| End November or beginning of December 2018 (duration 1 or 2 days depending on company’s size) | Visit to the company for internal audit/confirmation of company’s requirements.  Establishment of management system’s requirements according to company’s needs. | EU Partners + Jordanian Partners |
| 1/1-30/1/19 | Finalization of requested Food safety management system.  Delivering of requested Food safety management system to company. | EU Partners + Jordanian Partners |
| Training of company’s staff according to requested Food safety management system | Jordanian partners |
| 1/2 – 30/6/19 | Implementation of food safety management system according to the standard requirement.  Regular consultation with Jordanian partners. | Company (supported by Jordanian partners) |
| Monthly follow-up concerning the implementation of the selected Food safety management system. | AUA and BAU |
| **WP4.3 – IMPLEMENTATION of FOOD SAFETY AND QUALITY MANAGEMENT SYSTEMS** | | |
| **PERIOD** | **ACTIVITY** | **PARTICIPANTS** |
| Beginning of July 2019 (duration 1 or 2 days depending on company’s size) | Visit to the company for full independent audit according to the management system selected. | EU Partners + Jordanian Partners |
| **WP4.4 – ESTABLISHMENT OF POSSIBLE CORRECTIVE ACTIONS** | | |
| **PERIOD** | **ACTIVITY** | **PARTICIPANTS** |
| Until 31/7/19 | Establishment of corrective actions for the non-conformities identified in the independent audit (WP4.3). | Company (supported by Jordanian partners) |