## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP1 – Development of the training materials |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal | Number of e-books produced; Number of videos produced; Number of posters produced. |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Definition and validation of the e-book in the e-form | January 2017 | February 2017 | Partner institutions | Preparation for the initial project meeting | --- |
| 1.2 | Definition and validation of structure of the videos | January 2017 | February 2017 | Partner institutions | Preparation for the initial project meeting | --- |
| 1.3 | Definition and validation of the posters | January 2017 | February 2017 | Partner institutions | Preparation for the initial project meeting | --- |
| 1.1 | Definition and validation of the e-book in the e-form | 23-02-2017 | 25-02-2017 | Jordan | Discussion and preliminary definition and validation of e-books contents. Definition of specific teams for the development of each e-book. | Team list by e-book to be developed. |
| 1.2 | Definition and validation of structure of the videos | 23-02-2017 | 25-02-2017 | Jordan | Discussion and preliminary definition and validation of video contents. Definition of specific teams for the development of each video. | Team list by video to be developed. |
| 1.3 | Definition and validation of the posters | 23-02-2017 | 25-02-2017 | Jordan | Discussion and preliminary definition and validation of poster contents. Definition of specific teams for the development of each poster. | Team list by poster to be developed. |
| 1.1 | Definition and validation of the e-book in the e-form | 26-02-2017 | 31-03-2017 | Partner institutions | Development and validation of the detailed content and structure of each e-book. | Index of contents for the 8 e-books to be produced. |
| 1.2 | Definition and validation of structure of the videos | 26-02-2017 | 31-03-2017 | Partner institutions | Development and validation of the detailed content and structure of each video. | Index of contents and structure for the 5 videos to be produced. |
| 1.3 | Definition and validation of the posters | 26-02-2017 | 31-03-2017 | Partner institutions | Development and validation of the detailed content and structure of each poster. | Index of contents and structure for the 5 posters to be produced. |
| 1.4. | Production of e-books | 01-04-2017 | 30-06-2017 | Partner institutions – team groups | Writing of the English version of the books - in progress | --- |
| 1.5 | Production of videos | 01-04-2017 | 30-06-2017 | Jordan | Development and production of the videos – in progress | --- |
| 1.6 | Development and production of posters | 01-04-2017 | 30-06-2017 | Jordan | Development and production of the posters - in progress | --- |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |
| 1.4. | Production of e-books | 01-07-2017 | 30-09-2017 | Partner institutions – team groups | Writing of the English version of the books – conclusion. | English versions of the 8 e-books (in paper). |
| 1.5 | Production of videos | 01-07-2017 | 30-09-2017 | Jordan | Development and production of the videos – conclusion. | 5 videos on the defined topics. |
| 1.6 | Development and production of posters | 01-07-2017 | 30-09-2017 | Jordan | Development and production of the posters -conclusion. | Development and production of the 8 posters. |
| 1.4. | Production of e-books | 01-10-2017 | 31-12-2017 | Partner institutions – jordanian team members | Writing of the Arabic version of the books. | English versions of the 8 e-books (in paper). |
| 1.4. | Production of e-books | 01-10-2017 | 31-10-2017 | Partner institutions – team groups | Identification of the links to be established in the e-books that will allow the navigation in each e-book, in order to prepare the work to up-load the e-books: in English versions. | 8 ebooks (paper versions) with the definition/list of the links to be considered – in the English versions. |
| 1.4. | Production of e-books | 01-11-2017 | 30-11-2017 | Partner institutions – team groups | Identification of the links to be established in the e-books that will allow the navigation in each e-book, in order to prepare the work to up-load the e-books: in Arabic versions. | 8 ebooks (paper versions) with the definition/list of the links to be considered – in the Arabic versions. |
| 1.4. | Production of e-books | 01-11-2017 | 31-03-2018 | Jordan | Insertion of the e-books on the FOODQA website with navigation links. | 8 e-books up-loaded in FOODQA website with navigation links operational. |
| 1.7 | Validation of the training materials developed | September 2017 | October 2017 | 2nd project meeting | Validation of e-books, videos and poster before final production. To be done during the second project meeting and week immediately after. | Document of approval by all partners. |

Changes that have occurred in this result since the original proposal:

Any.