## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP1 – Development of the training materials |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal | Number of e-books produced; Number of videos produced; Number of posters produced. |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Definition and validation of the e-book in the e-form | 23-02-2017 | 25-02-2017 | Jordan | Completed: The contents of the 8 e-books have been approved | Number of e-books |
| 1.2 | Definition and validation of structure of the videos | 23-02-2017 | 25-02-2017 | Jordan | Completed: The contents of the 5 videos have been approved. | Number of videos |
| 1.3 | Definition and validation of the posters | 23-02-2017 | 25-02-2017 | Jordan | Completed: The contents of the 8 posters have been approved. | Number of posters |
| 1.4. | Production of e-books | 01-04-2017 | 30-03-2018 | Partner institutions – team groups | - 5 e-books have been produced - The remaining 3 e-books will be produced before the deadline | --- |
| 1.5 | Production of videos | 01-04-2017 | 30-09-2017 | Jordan | - Some videos have been produced - The delay was due to the decision on integrating the e-books, videos, and posters - Other videos will be produced by Mid Feb. 2018 | --- |
| 1.6 | Development and production of posters | 01-04-2017 | 30-09-2017 | Jordan | - Some posters have been produced - The delay was due to the decision on integrating the e-books, videos, and posters - Other posters will be produced by Mid Feb. 2018 | --- |
| 1.4. | Production of e-books | 01-07-2017 | 30-09-2017 | Partner institutions – team groups | Writing of the English version of the books – conclusion. | English versions of the 8 e-books (in paper). |
| 1.5 | Production of videos | 01-07-2017 | 30-09-2017 | Jordan | Development and production of the videos – conclusion. | 5 videos on the defined topics. |
| 1.6 | Development and production of posters | 01-07-2017 | 30-09-2017 | Jordan | Development and production of the posters -conclusion. | Development and production of the 8 posters. |
| 1.7 | Validation of the training materials developed | September 2017 | October 2017 | 2nd project meeting | Completed: all developed materials have been validated. | Document of approval by all partners. |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |
| 1.4. | Production of e-books | 01-07-2017 | 30-03-2018 | Partner institutions – team groups | Production of all 8 e-books | Number of e-books |
| 1.5 | Production of videos | 01-07-2017 | 15-02-2018 | Jordan | Development and production of all the videos – conclusion. | Number of the videos |
| 1.6 | Development and production of posters | 01-07-2017 | 15-02-2018 | Jordan | Development and production of all the posters -conclusion. | Number of the poster. |

Changes that have occurred in this result since the original proposal: