## Slide 1
Fostering Academia-Industry Collaboration in Food Safety and Quality (FOODQA)
Prof. Fahmi Abu Al-Rub, Project Coordinator, JUST
Third Management Meeting
January 21-24, 2018
Porto-Portugal

## Slide 2
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Duration: 01-01-2017 to 31.4.2018
1.1 Definition and validation of the books in e-form. | Status: COMPLETED Eight e-books have been identified An e-book leader has been assigned for each e-book The materials have been distributed among the partners according to their competencies All of the e-books’ materials have been prepared All books have been validated All books have been

## Slide 3
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Duration: 01-01-2017 to 31.4.2018
1.2 Definition and validation of structure of the videos | Status: Pending Five videos have been identified A “video” leader has been assigned for each video The videos have been distributed among the partners according to their competencies All videos’ materials have been finalized, validated, and approved Production of the videos: where? Some of the videos have been produced Videos will be distributed for the Academia-Industry Council members

## Slide 4
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Duration: 01-01-2017 to 31.4.2018
1.3 Definition and validation of posters. | Status: Pending Eight posters have been identified A “poster” leader has been assigned for each poster The posters have been distributed among the partners according to their competencies All posters’ materials have been finalized, validated, and approved Some partners have prepared the assigned posters Production of the posters: where? Posters will be distributed for the Academia-Industry Council members

## Slide 5
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Duration: 01-01-2017 to 31.4.2018
1.4 Production of e-book | Status: Pending Most of the e-books have been prepared and produced RISK: deadline is 31.3.2018 Next: Production of all books Translation of all books Distribution of all books to Academia Industry Council members

## Slide 6
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Duration: 01-01-2017 to 31.4.2018
1.5 Production of videos | Status: Pending Most of the videos have been produced Some of the videos have been produced RISK: deadline is 30.9.2017 Next: Production of all videos Distribution of all videos to Academia Industry Council members

## Slide 7
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Duration: 01-01-2017 to 31.4.2018
1.6 Development and production of the Posters | Status: Most of the 8 posters have been prepared RISK: deadline is 30.9.2017 Next: Production of all posters Distribution of all posters to Academia Industry Council members

## Slide 8
WP1: DEVELOPMENT OF TRAINING MATERIAL (Lead: P&B)
Videos & Posters |  | Content | Res. Partner | Text | Images
 | 1. | Hand washing | Split | Done | JFDA
 | 2. | Cleaning and disinfection | SPLIT | Done | MonoJo
 | 3. | Pest control | BAU | Done | BAU
 | 4. | Temperature control | P&B | Done | JUST
 | 5. | Control of reception of raw materials | JFDA | Done | JU
Posters | 6. | Food spoilage | UniTe | DONE | Mut’ah
 | 7. | Food Safety | P&B | Done | UJ
 | 8. | Hazard analysis | AUA | DONE | MonoJo

## Slide 9
WP2: Development of training courses (Lead: UNITE)
Duration: 01-01-2017 to 30.9.2019
2.1 Definitions of the educational dossiers and contents for the 6 training courses | Status: Completed Educational materials have been identified A leader has been assigned for each training material The materials have been distributed among the partners according to their competencies

## Slide 10
WP2: Development of training courses (Lead: UNITE)
Duration: 01-01-2017 to 30.9.2019
2.2 Developments of the 6 training courses | Status: Completed Educational materials have been prepared and approved

## Slide 11
WP2: Development of training courses (Lead: UNITE)
Duration: 01-01-2017 to 30.9.2019
2.3 Validation of the educational dossiers and contents for the 8 in-room training courses-pilot training courses | Status: Completed All the educational materials have been validated and approved

## Slide 12
WP2: Development of training courses (Lead: UNITE)
Duration: 01-01-2017 to 30.9.2019
2.4-2.7 Detailed definition of the model of e-learning courses | No significant progress has been noticed RISK: No material has been prepared!! Next: All courses should be prepared and verified Agree on the e-courses

## Slide 13
WP2: Development of training courses (Lead: UNITE)
Duration: 01-01-2017 to 30.9.2019
2.8 Installations of the e-library and e-learning facilities | Status: 1. Food Safety Centers have been established 2. The centers have been equipped with PCs Next: All courses should be prepared and verified Installations of the e-library and e-learning facilities

## Slide 14
WP3: Training of academia and industry (MONOJO, JUST)
Duration: 01-03-2017 to 30.9.2019
3.1 Preparation and organization of the seminars | Status: 1. Three seminars materials have been prepared; one by JFDA, and two by MONOJO 2. The seminars have been organized in the second AIC meeting which was held in Nov., 2017.

## Slide 15
WP3: Training of academia and industry (MONOJO, JUST)
Duration: 01-03-2017 to 30.9.2019
3.2 Realisation of the seminars | Status: 1. Three seminars materials have been prepared; one by JFDA, and two by MONOJO 2. The seminars have been organized in the second AIC meeting which was held in Nov., 2017. Next: All materials should be prepared and verified

## Slide 16
WP3: Training of academia and industry (MONOJO, JUST)
Duration: 01-03-2017 to 30.9.2019
3.3 Preparation and organization of the training courses | No significant progress has been noticed RISK: No material has been prepared!! Next: All materials should be prepared and verified

## Slide 17
WP3: Training of academia and industry (MONOJO, JUST)
Duration: 01-03-2017 to 30.9.2019
3.4 Realisation of the training courses | No significant progress has been noticed RISK: No material has been prepared!! Next: All materials should be prepared and verified

## Slide 18
WP4: Pilot of implementation of food safety and quality management systems (JFDA, JUST)
Duration: 01-03-2017 to 30.9.2019
4.1 Preparation of food safety and quality management systems | No significant progress has been noticed RISK: No material has been prepared!! Next: All materials should be prepared and verified

## Slide 19
WP4: Pilot of implementation of food safety and quality management systems (JFDA, JUST)
Duration: 01-03-2017 to 30.9.2019
4.2 Implementation of food safety and quality management systems | No significant progress has been noticed RISK: No material has been prepared!! Next: All materials should be prepared and verified

## Slide 20
WP4: Pilot of implementation of food safety and quality management systems (JFDA, JUST)
Duration: 01-03-2017 to 30.9.2019
4.3 Conducting independent audits | No significant progress has been noticed RISK: No material has been prepared!!

## Slide 21
WP5: DISSEMINATION & EXPLOITATION (HTWK, Co-Lead: JUST, MONOJO, UJ)
Duration: 01-01-2017 to 30.9.2019
Dissemination and Sustainability Plans | Status: 1. HTWK prepared the project dissemination plant 2. UJ has prepared a draft of the sustainability plan Next: 1. UJ to finalize the sustainability plan

## Slide 22
WP5: DISSEMINATION & EXPLOITATION (HTWK, Co-Lead: JUST, MONOJO, UJ)
Duration: 01-01-2017 to 30.9.2019
5.1-5.4 FoodQA website 5.5 Project news letter | http://foodqa.just.edu.jo/Pages/default.aspx http://foodqa.just.edu.jo/Pages/newsletter.aspx Second issue have been produced Third issue to be produced in April 2018

## Slide 23
WP5: DISSEMINATION & EXPLOITATION (HTWK, Co-Lead: JUST, MONOJO, UJ)
Duration: 01-01-2017 to 30.9.2019
5.6-5.8 definition of the academia-industry council | The companies to be invited to join the Academia Industry Council (AIC) have been identified Invitations have been prepared and sent to AIC have been prepared and sent The first meeting was organized in May The second meeting was organized in November 2017 Next: The third meeting will be organized in April-May 2018

## Slide 24
WP6: Quality (CRE.THI.DEV, MU)
Duration: 01-01-2017 to 30.9.2019
6.1 Establish the Quality committee 6.2 Develop a monitoring, evaluation, and quality plan 6.3 Write progress reports that elaborate the progress of the project and address it to the project coordinator | The Quality Committee was established during the kick-off meeting 1. CRE.THI.DEV has developed the quality and monitoring plan 2. The plan was approved by all partners First progress reports on the started WPs have been prepared by each WP leader These reports were sent to the external monitor The Second progress reports have been prepared and sent to the external monitor Next: 1. Third progress reports to be prepared and sent before April 2018

## Slide 25
WP6: Quality (CRE.THI.DEV, MU)
Duration: 01-01-2017 to 30.9.2019
6.4 Hire External Monitor | The selection of the external monitor was approved by the Quality WP leader

## Slide 26
Discussion (Questions and Concerns)

## Slide 27
Thanks