## Table of achieved / planned results

|  |  |
| --- | --- |
| **Title and reference number of the work package (WP)** | ***2*** |
|  |  |
| **Indicators of achievement and or/performance as indicated in the project proposal** | Quantitative:* Number of training courses developed
* Creation of a model of e-learning training courses
* Number of pilot training courses carried out
* Number of e-learning courses developed

Milestones* Materials for training courses prepared
* E-learning courses available in the web portal in the web portal
* List of attendance in the seminars and training courses
* Evaluation of the trainees of the training courses
 |

**Activities carried out to date to achieve this result:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Activity N°** | **Activity** **Title** | **Start date** | **End date** | **Place** | **Description of the activity carried out** | **Specific and measurable indicators of achievement** |
| *2.1*  | ***Definitions of the educational dossiers and contents for the 8 training courses.***  | *M1* | *M12* | *UNITE* | - The list of the training courses have been identified.- Development of the form for the syllabus of each training course to be filled in by each partner- The database for planning the testing of the training courses haven been developed- All syllabi of the training courses have been collected.  | - syllabus form made available to partners- Database available for partners to be filled in |
|

|  |
| --- |
| 2.2  |
|  |  |

 | ***Developments of the 8 in-room training courses*** | ***M12*** | ***M18*** | Partners locations | Based on outcomes task 2.1, the educational dossiers of 8 training courses have been developed and training have been conducted in EU institutions:-P&B Training: January 2018-Teramo Training: January-February 2018-AUA Training: April 2018-Split training: September 2018.  | Educational dossier made available |
| 2.3  | **Validation of the educational dossiers and contents for the 8 in-room training courses-pilot training courses** | M18 | M21 | Partners locations | Validation of the educational dossiers and contents (syllabus) for the remaining five training courses, by consortium and by the Academia- industry council and final validation of each one of the materials has been carried out by the training at EU and the training of AIC members. will be done through pilot training actions. | *Educational dossier of the three courses are made available* |
| 2.4. | **Detailed definition of the model of e-learning courses.**  | M12 | M18 | Partners locations | The 3 e-learning training courses to be used as a pilot to test the model of e-learning to be built haven developed. The 3 e-learning training courses that have been developed are: 1. Food safety management systems-ISO 22000:2005. 2. Quality management systems-ISO 9001:2008. 3. Personnel Hygiene. E-learning training courses will be made available in an e-learning platform (Task 2.8)  | Educational dossier of 3 e-learning courses made available |
| 2.5 | **Definition and validation of content of the 2 e-learning courses**  | M18 | M19 | Partners locations | The contents of the e-courses have been validated by the partners and through students.  | Validation by e-learning courses carried out |
| 2.6. | **Development of the 3 e-learning courses**  | M20 | M27 | Partners locations | The 3 e-learning training courses have been developed.  | e-learning courses delivered at the partner study programmes |
| **2.7** | **Validation of the 2 e-learning courses.**  | M20 | M36 | Partners locations | Validation of the 3 e-learning training courses has been carried out by the consortium and the Academia-industry council through pilot training action. All partners tested the three e-courses by offering them to their students. | Validation of the e-learning courses done |
| 2.8 | **Installations of the e-library and e-learning facilities.**  | MX | M27 | Project website | The FOODQA platform is in continuous updating. The platform contains all e-books, training materials and courses, MOOCS, etc. Log-on system of the library ensures the saving of the copyright rules in respect to electronic subscription systems and the book placed in the e-library.  | E-learning platform made available and electronic files and documents available |

**Activities to be carried out to achieve this outcome (before the end of the project)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Activity N°** | **Activity** **Title** | **Start date** | **End date** | **Place** | **Description of the activity to be carried out** | **Specific and measurable indicators of progress** |
|  |  |  |  |  |  |  |
| **2.7** | **Validation of the 2 e-learning courses.**  | M20 | M36 | Partners locations | Continue Validation of the 3 e-learning training courses by the consortium and the Academia-industry council through pilot training action.  | Validation of the e-learning courses done |
| 2.8 | **Installations of the e-library and e-learning facilities.**  | MX | M27 | Project website | Update the contents of the platform  | E-learning platform made available and electronic files and documents available |

**Changes that have occurred in this result since the original proposal:**