## Table of achieved / planned results

|  |  |
| --- | --- |
| **Title and reference number of the work package (WP)** | ***2*** |
|  |  |
| **Indicators of achievement and or/performance as indicated in the project proposal** | Quantitative:* Number of training courses developed
* Creation of a model of e-learning training courses
* Number of pilot training courses carried out
* Number of e-learning courses developed

Milestones* Materials for training courses prepared
* E-learning courses available in the web portal in the web portal
* List of attendance in the seminars and training courses
* Evaluation of the trainees of the training courses
 |

**Activities carried out to date to achieve this result:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Activity N°** | **Activity** **Title** | **Start date** | **End date** | **Place** | **Description of the activity carried out** | **Specific and measurable indicators of achievement** |
| *2.1*  | ***Definitions of the educational dossiers and contents for the 8 training courses.***  | *M1* | *M12* | *UNITE* | - The list of the training courses to be developed has been identified and defined. This was done based on a survey on local needs of the food industry in Jordan which was completed by more than 40 companies- The template for the syllabus of each training course to be filled in by each partner has been developed and approved by the Quality Committee- Development of a database for planning the testing of the training courses - Collection of syllabi of n. 8 training courses  | - Survey for local needs developed (n. 1)- Number of companies completed the survey (n. 40)- Report on survey analysis completed (n. 1)- Syllabus form made available to partners (n. 8)- Database available for partners to be filled in |
|

|  |
| --- |
| 2.2  |
|  |  |

 | ***Developments of the 8 in-room training courses*** | ***M12*** | ***M18*** | Partners locations | Based on outcomes task 2.1, the educational dossiers of 8 training courses that will take place between January and September 2018 at the European partners institutions have been developed and approved. Exact timing and location has been defined for each training course. All the EU partners have been involved. | Educational dossier made available (n. 8) |
| 2.3  | **Validation of the educational dossiers and contents for the 8 in-room training courses-pilot training courses** | M18 | M21 | Partners locations | The training courses have been developed and validated by trainees. In particular * “Food safety management systems” (22-26 Jan 2018, Porto-PT)
* “Cleaning and disinfection” and
* “Food Safety Hazards” (29 Jan-2nd Feb 2018, Teramo-IT)
* “Quality management systems (Standard for quality management systems-ISO 9001:2008: management responsibilities, resources management, product realisation, measurement, analysis and improvement” (15-22 April 2019, Athens-Greece)
* “Quality management tools (Flow charts, cause-effect diagram, pareto diagram, control chart, value analysis, FMEA-failure Mode and Effect Analysis, quality cost, Brainstorming, Benchmarking, Balanced scorecard” (15-22 April 2019, Athens-Greece)
* “Food safety management systems-ISO 22000:2015” (22-26 Jan 2018, Porto-PT).
* Personnel Hygiene (September 2018, Split, Croatia).
* Pest Control (September 2018, Split, Croatia)
* Design and construction of Food premises (September 2018, Split, Croatia)

Validation of the educational dossiers and contents (syllabus) for the training courses, by consortium and by the Academia- industry council and final validation of each one of the materials has been carried out by the training at EU and the training of AIC members. | n. 8 Educational dossier of the courses are made available  |
| 2.4. | **Detailed definition of the model of e-learning courses.**  | M12 | M18 | Partners locations | The 3 e-learning training courses to be used as a pilot to test the model of e-learning to be built haven developed. The 3 e-learning training courses that have been developed are: 1. Food safety management systems-ISO 22000:2005. 2. Quality management systems-ISO 9001:2008. 3. Personnel Hygiene. Another fourth training course was implemented for JUST students: HACCPE-learning training courses will be made available in an e-learning platform (Task 2.8)  | Educational dossier of 3 e-learning courses made available |
| 2.5 | **Definition and validation of content of the 2 e-learning courses**  | M18 | M19 | Partners locations | The contents of the e-courses have been validated by the partners and through students.  | Validation by e-learning courses carried out |
| 2.6. | **Development of the 3 e-learning courses**  | M20 | M27 | Jordan | The 3 e-learning training courses have been developed.  | e-learning courses delivered at the partner study programmes |
| **2.7** | **Validation of the 2 e-learning courses.**  | M20 | M36 | Partners locations | Validation of the 3 e-learning training courses has been carried out by the consortium and the Academia-industry council through pilot training action. All partners tested the three e-courses by offering them to their students. | Validation of the e-learning courses done |
| 2.8 | **Installations of the e-library and e-learning facilities.**  | MX | M27 | JUST | The FOODQA platform is in continuous updating. The platform contains all e-books, training materials and courses, MOOCS, etc. Log-on system of the library ensures the saving of the copyright rules in respect to electronic subscription systems and the book placed in the e-library.  | E-learning platform made available and electronic files and documents available |

**Activities to be carried out to achieve this outcome (before the end of the project)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Activity N°** | **Activity** **Title** | **Start date** | **End date** | **Place** | **Description of the activity to be carried out** | **Specific and measurable indicators of progress** |
|  |  |  |  |  |  |  |

**Changes that have occurred in this result since the original proposal:**

Three courses and not two courses as was planned have been developed and implemented.