## Table of achieved / planned results

|  |  |
| --- | --- |
| **Title and reference number of the work package (WP)** | **WP 5: DISSEMINATION & EXPLOITATION** |
|  |  |
| **Indicators of achievement and or/performance as indicated in the project proposal** | 1. Creation of Academia industry council (AIC) 2. Building project website 3. Activities on the website 4. Number of visitors of the project website 5. Number of workshops and meetings for AIC 6. Number of participants in the AIC meetings and workshops 7. Number of newsletters issued |

**Activities carried out to date to achieve this result:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Activity N°** | **Activity**  **Title** | **Start date** | **End date** | **Place** | **Description of the activity carried out** | **Specific and measurable indicators of achievement** |
| 5.1 | Definition of the web portal | 01.01.2017 | 31.03.2019 | JO,  DE | The content and structure of contents and requirements of the web portal was defined was defined and fimalized. | Website  Information on website  Number of learning materials |
| 5.2 | Development/validation of the architecture of the web-portal. | 01.01.2017 | 31.03.2019 | JO,  DE | The website of the project was developed by JUST the coordinator of the project.  [http://foodqa.just.edu.jo](http://foodqa.just.edu.jo/)  JUST has defined the architecture of the web-portal and the architecture was approved before  the beginning of the software development.  The website contains information about the project, activities, partners, academia-industry council and training activities. | Website  Reports |
| 5.3 | Development and validation of the web-portal | 01.01.2017 | 31.03.2019 | JO,  DE | BAU, UJ and MU are the mainly partners involved in the validation process of the web-portal and make the regular follow up with JFDA and JUST during the development of the web-portal. | Reports  Information on website |
| 5.4 | Gathering information. | 01.01.2017 | 31.03.2019 | JO | Partners in the project identified the relevant information and sources of information that would  be of interest to be supported or linked Lo the web-portal. The menu DATABASE contain information about these source.  http://foodqa.just.edu.jo/Pages/Database.aspx | Information in DATABASE  Number of sources  reports |
| 5.5 | project news letter | 01.01.2017 | 31.03.2019 | JO,  DE | 4 newsletters are created. It contains all information about the project activities. | Number of newsletters |
| 5.6 | definition of the academia-industry council. | 01.01.2017 | 31.03.2019 | JO | The Academia-Industry Councils was established.  Please see http://foodqa.just.edu.jo/Pages/FoodqaAIC.aspx | Number of member in Academia-Industry Councils |
| 5.7 | invitations to representatives for the council. | 01.01.2017 | 31.03.2019 | JO | Part of the process of invitation of representatives for the Academia Industry Council is conducted | reports |
| 5.8 | Council meeting. | 01.01.2017 | 31.03.2019 | JO | The Academia — Industry Council continued its bi-annual meetings and trainings. | Reports  Meeting Agenda  Number of participants |
| 5.9 | Definition or the model of Associated of the FoodQA Centres. | 01.01.2017 | 31.03.2019 | JO | A **model of Associated of the FoodQA Centres** to support and promote the establishment of long term  relation between academia and industry was developed by UJ. | Reports |
|  |  |  |  |  |  |  |

**Activities to be carried out to achieve this outcome (before the end of the project)**

| **Activity N°** | **Activity**  **Title** | **Start date** | **End date** | **Place** | **Description of the activity to be carried out** | **Specific and measurable indicators of progress** |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Definition of the web portal | 01.01.2017 | 31.03.2019 | JO,  DE | Continue and Update of the information on website | Website  Information on website  Number of learning materials |
| 5.2 | Development/validation of the architecture of the web-portal. | 01.01.2017 | 31.03.2019 | JO,  DE | Continue and Update of the information on website | Website  Reports |
| 5.3 | Development and validation of the web-portal | 01.01.2017 | 31.03.2019 | JO,  DE | Continue and Update | Reports  Information on website |
| 5.4 | Gathering information. | 01.01.2017 | 31.03.2019 | JO | Continue and Update of Gathering information | Information in DATABASE  Number of sources  reports |
| 5.5 | Project newsletter | 01.01.2017 | 31.03.2019 | JO,  DE | Continue by dissemination of the project | Number of newsletters |
| 5.6 | definition of the academia-industry council. | 01.01.2017 | 31.03.2019 | JO | Continue and Update the activities with academia-industry council | Number of member in Academia-Industry Councils |
| 5.7 | invitations to representatives for the council. | 01.01.2017 | 31.03.2019 | JO | Continue and update the invitations to representatives for the council | reports |
| 5.8 | Council meeting. | 01.01.2017 | 31.03.2019 | JO | Continue the Meetings | Reports  Meeting Agenda  Number of participants |
| 5.9 | Definition or the model of Associated of the FoodQA Centres. | 01.01.2017 | 31.03.2019 | JO | Test the model of Associated of the FoodQA Centres and the equipment in the cenetrs | Reports |

**Changes that have occurred in this result since the original proposal:**

|  |
| --- |
|  |