## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP 6 (QUALITY) |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal |  |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Establish the Quality committee | 01/01/2017 | 23/2/2017 | Jordan | The Quality Committee was established during the kickoff meeting | 1x Quality Committee through the Minutes of the kickoff meeting |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |
| 6.2 | Develop a monitoring, evaluation, and quality plan | 01/01/2017 | 30/06/2017 | Greece | The Quality Plan for the project will be developed and distributed by July 15, 2017 | 1 x Quality Plan |
| 6.3 | Write progress reports that elaborate the progress of the project and address it to the project coordinator | 01/01/2017 | 31/12/2019 | Greece | Every 6 months progress reports will be elaborated. Every 18 months evaluation reports will be elaborated (at midterm and at the end of the project) | 6 x progress reports 2 x evaluation reports |
| 6.4 | Hire External Monitor | 01/01/2017 | 31/12/2017 | Jordan | An external monitor will be hired to verify the quality of the project | 1x evaluation report by external auditor |

Changes that have occurred in this result since the original proposal:

The deadline for the hiring of the external monitor was incorrectly set at 31/12/2019; the correct is 31/12/2017. The deadline for the Quality Plan was incorrectly set at 31/12/2019; the correct is 30/06/2017.