## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP 6 (QUALITY) |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal | - List of Quality Committee members - Monitoring, evaluation, and Quality plan developed - Progress reports are prepared and submitted - Subcontract with external evaluators - Reports of external evaluators - Quality and evaluation reports. |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Establish the Quality committee | 01/01/2017 | 23/2/2017 | Jordan | The Quality Committee was established during the kickoff meeting | 1x Quality Committee through the Minutes of the kickoff meeting |
| 6.2 | Develop a monitoring, evaluation, and quality plan | 01/01/2017 | 30/06/2017 | Greece | The Quality Plan for the project was developed and distributed on July 15, 2017. Amendments to the Quality plan were deemed necessary, as a result of the Midterm evaluation. The changes to the QP were included in the 2nd version (March 2018). | 1 x Quality Plan |
| 6.3 | Write progress reports that elaborate the progress of the project and address it to the project coordinator | 01/01/2017 | 31/12/2019 | Greece | A progress report was elaborated for the first 6 months by all task leaders in July 2017. A 2nd progress report was elaborated for the 2nd semester in January 2017. A 3rd progress report was elaborated in April 2018. A 4th Progress report was elaborated in October 2018. A 5th Progress report was elaborated in April 2019 | 6 x progress reports (every 6 months) 2 x evaluation reports (18 months, 36 months) |
| 6.4 | Hire External Monitor | 01/01/2017 | 31/12/2017 | Jordan | An external monitor was hired to verify the quality of the project and made an evaluation. Evaluation results were distributed to all partners to make necessary amendments. | 1x evaluation report by external auditor |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |
| 6.3 | Write progress reports that elaborate the progress of the project and address it to the project coordinator | 01/01/2017 | 31/12/2019 | Greece | Every 6 months progress reports must be elaborated. 3 more reports are to be elaborated. The report at Final midterm is to be elaborated by October 2019. | 6 x progress reports (every 6 months) 2 x evaluation reports (18 months, 36 months) |

Changes that have occurred in this result since the original proposal: