## Table of achieved / planned results

| Title and reference number of the work package (WP) | DISSEMINATION & EXPLOITATION |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal | Creation of Academia industry council |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Definition of the web portal | 31-01-2017 | 31-03-2017 | Jordan | Website of the project has been created: http://foodqa.just.edu.jo/Pages/default.aspx It consists of all information, activities, documents, etc., related to the project. The site includes information on the different types of links, such as: link to RASFF (Rapid Alert System for Food and Feed) and TRACES: links to Codex Alimentarius: Links to national and European Food Safety Agencies: links to EU Legislation. Links to scientific and technical publishers. It will also include list of technical documents related to food safety per topic (e.g. labelling. additives. materials in contacts with foods. (GMO’s, contaminants) and per food industrial sector meat, Dairy, Fish, Cereals, Beverages, Water, Fruit and Vegetables, vegetable oils) and list of technical documents related to food quality and quality management systems (e.g. quality standards, total quality management. quality management tools). | - Website created - Number of visitors |
| 5.2 | Development/validation of the architecture of the web-portal | 31-01-2017 | 30-06-2017 |  | Based on the requirement/functionalities determined in Activity 5.1 and in the detailed structures of contents, JUST has defined the architecture of the web-portal. | Working and functional website |
| 5.3 |  |  |  |  |  |  |
| 5.5 | Development of the project news letter | 15.01.2017 | End of the project | Jordan- EU | Producing a newsletter for the project activities every six months. Issue number 1 is completed and published on the FOODQA website | 6 issues of newsletters at the end of the project |
| 5.6 | Definition of academia – industry council |  | 31.05.2017 | Jordan | Academia Industry Council (AIC) that includes representative both from academia (all FoodQA partners and more than 40 Food Industries companies) has been established. The FoodQA network has also been published on the FoodQA website. | -Establishment of the AIC - Number of companies joined the AIC - FoodQA network |
| 5.7 | invitation to representatives for the council | 15.10.20.16 | 31.5.2017 | Jordan | All JO partners have been involved in inviting food companies to attend the AIC first meeting | -Number of invitations |
| 5.8 | Council meeting |  | 31.05.2017 | Jordan | The first meeting for Academia industry council was held before the due date in a hotel in Amman. More than 50 participants representing the different food industries and companies in Jordan attended the first meeting. During the meeting, Prof. Abu Al-Rub, introduced FoodQA to the participants and invited them to join the FoodQA network. | - Number of AIC meetings - Number of participants in each meeting |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |
| 5.3 | Development and validation of the web-portal | 31-01-2017 | 31-12-2017 | Jordan | This activity will be coordinated by the JO partners. UJ, BAU and MU will be mainly involved in the validation process of the web-portal and will make the regular follow up with JFDA and JUST during the development of the web-portal. The Academia- Industry Councils will be requested to provide their comments and to support the validation of the web-portal. | Establishment of the FoodQA portal |
| 5.4 | Gathering information | 31-01-2017 | 31-12-2017 | Jordan | This activity will be coordinated by the partner UJ based in its previous experience in this field. The objective is, in articulation to the Partner Countries universities, identify’ relevant information and sources of information that would be of interest to be supported or linked to the web-portal. The idea is that this would support the development of an information service to be provided to companies. This information service is expected to be one of the pillars of the sustainability of the FoodQA Centres. This service would include regular services such as in the area of food legislation or specific data search on request of the client. | - Information gathered - Number of companies visited the website |
| 5.9 | Definition or the model of Associated of the FoodQA Centres | 31-01-2017 | 31-12-2017 | Jordan | To support and promote the establishment of long term relation between academia and industry it is envisaged to create food association between food industries and the FoodQA Centres. These companies or associations would be able to benefit from the services of the FoodQA Centres with some advantages, such as discounts in the services. It is also expected that, in a second moment, at least half of the representatives of the industry would be selected by the industrial companies Associated of the FoodQA Centres during this activity the model of Associated of the FoodQA Centres will be defined and validated. The Academia—Industry Council will be invited to give their comments in this issue. | Number of associations Number of services provided to the companies |

Changes that have occurred in this result since the original proposal: